## Sheet1
Tasks | Assigned | Estimated (days) | Remaining (days) | Jira ID | Sprint | Status | Comments | Start Date | End Date
Research solutions | Bao Nguyen | 2 |  | IVPORTAL-11 | 13 | Closed
Apply to Document Portlet (Prospect screen) | Hai Vu | 3 |  | IVPORTAL-73 | 14 | Closed
Apply to User Profile portlet | Hai Vu | 3 | 1 | IVPORTAL-72 | 14,15 | Planned
Migrate Portlet Configuration to V3
Adapt BI endpoint change | Phong Nguyen | 0.5
Email
Update service (client, policy)
Upgrade dropdown long list to popup long list
Enhance security for login functionality | Dung Pham |  |  | IVPORTAL-64 |  | Closed
Enhancement for Login portlet | Dung Pham | 4 |  | IVPORTAL-65 | 14 | Closed
Enhancement for Change/Reset Password portlet | Dung Pham | 2 |  | IVPORTAL-74 | 14 | Closed
Enhancement for Registration portlet | Dung Pham | 3 |  | IVPORTAL-75 | 14 | Closed
Research build portal project with mvn in command line | Dung Pham | 2 | 1.5 | IVPORTAL-71 | 14,15 | Resolved
Design MSPMock and create some Policy Detail data | Long Hoang | 2 |  | IVPORTAL-91 | 14 | Closed
UC-IP-27 Policy Servicing - Endorsement & Surrender | Long Hoang
Understand Requirement | Long Hoang | 2 |  | IVPORTAL-92 | 14 | Closed
ENDORSEMENT - MOTOR | Long Hoang
Html design + Binding | Long Hoang
Policy Details screen | Long Hoang | 3 |  | IVPORTAL-93 | 14 | Closed
Confirmation screen | Long Hoang | 3 | 3 | IVPORTAL-94 | 15 | In Progress
Acknowledge screen | Long Hoang | 0.5 | 0.5 | IVPORTAL-100 | 15 | Planned
Call Backend to get data (compute, update) | Long Hoang | 2 | 2 | IVPORTAL-95 | 14,15 | Planned
Write controller service to filter policy eligible for endorsement or surrender | Qui Huynh | 0.5 | 0.5 | IVPORTAL-185 | 15 | Planned
Implement javascript functions to compare change in endorsment | Long Hoang | 1 | 1 | IVPORTAL-186 | 15 | Planned
Navigate to Payment Process screen | Long Hoang | 0.5 | 0.5 | IVPORTAL-187 | 15 | Planned
VPMS calculate premium for endorsement or surrender
After payment processing
Update status of policy to inforce | Long Hoang | 0.5 | 0.5 | IVPORTAL-188 | 15 | Planned
Generate PDF for Payment Slip and ePolicy | Long Hoang | 1 | 1 | IVPORTAL-189 | 15 | Planned
Call endorsement submission | Long Hoang | 2 |  | IVPORTAL-190
SURRENDER
Html design + Binding
Traditional screen | Qui Huynh | 2 | 2 | IVPORTAL-97 | 14,15 | In Progress
Confirmation screen | Qui Huynh | 0.5 | 0.5 | IVPORTAL-98 | 14,15 | Planned
Acknowledge screen | Qui Huynh | 0.5 | 0.5 | IVPORTAL-99 | 14,15 | Planned
Call Backend to get data (compute, update) | Qui Huynh | 2 | 3 | IVPORTAL-96 | 14,15 | Planned
Prepare mock data for policy due payment and policy renewal due in MSP | Long Hoang | 2 |  | IVPORTAL-110 | 14 | Closed
Migrate User Profile
Migrate backend | Hai Vu | [5 empty] | Don't do as Dung has done before
UC-IP-23 My Clients Policy Schedule (Renewal) | Nhut Nguyen |  |  | IVPORTAL-83 | 14 | Closed
Understand requirements | Nhut Nguyen | 0.5 |  | IVPORTAL-84 | 14 | Closed
My Clients Policy Payment Schedule portlet | Nhut Nguyen
Design UI | Nhut Nguyen | 1 |  | IVPORTAL-85 | 14 | Closed
Bind backend data to UI | Nhut Nguyen | 2 |  | IVPORTAL-86 | 14 | Closed
Call Backend to get policy list with payment due | Nhut Nguyen | 2 |  | IVPORTAL-87 | 14 | Closed
My Clients Policy Renewal Schedule portlet | Nhut Nguyen
Design UI | Nhut Nguyen | 1 |  | IVPORTAL-88 | 14 | Closed
Bind backend data to UI | Nhut Nguyen | 1.5 |  | IVPORTAL-89 | 14 | Closed
Call Backend to get policy list (motor/home only) with renewal due | Nhut Nguyen | 2 |  | IVPORTAL-90 | 14 | Closed
Migrate Policy Portfolio to V3 | Dang Nguyen
Migrate UI | Dang Nguyen | 4 |  | IVPORTAL-56 | 14 | Closed
Migrate Backend | Dang Nguyen | 6 | 2 | IVPORTAL-57 | 14,15 | Closed
Migrate Policy Servicing - Renewal | Minh Le
Migrate UI | Minh Le | 4 |  | IVPORTAL-62 | 14 | Closed
Migrate Backend | Minh Le | 6 |  | IVPORTAL-76 | 14 | Closed
Migrate My Policy Due for Renewal screen to V3 | Qui Huynh | 2 | 2 | IVPORTAL-130 | 15 | In Progress
UC-IP-25 Attention Required Document | Qui Huynh
Understand requirements | Qui Huynh | 1 |  | IVPORTAL-59 | 14 | Closed
Design UI | Qui Huynh | 1 |  | IVPORTAL-60 | 14 | Closed
Load Document infomation & binding | Qui Huynh
BI/ Quote | Qui Huynh | 3 |  | IVPORTAL-79 | 14 | Closed
Policy | Qui Huynh | 2 |  | IVPORTAL-80 | 14 | Closed
Salecase | Qui Huynh | [5 empty] | Will do later after salecase finished
Navigation for hyperlink for BI/ Quote/ Policy | Qui Huynh | 2 |  | IVPORTAL-81 | 14 | Closed
Design pop up for Contact Agent link | Qui Huynh | 1 |  | IVPORTAL-82 | 14 | Closed
Application Modules
Design UI | Phong Nguyen | 3 |  | IVPORTAL-67 | 14 | Resolved | Delete because will fixed in other issue
Navigation error on Portal Liferay | Khuong Nguyen | 1 |  | IVPORTAL-70 | 14 | Closed
Replicate Liferay database
Research solutions | Khuong Nguyen | 3 |  | IVPORTAL-77 | 14 | Closed
Apply to Liferay cloud server | Khuong Nguyen | 3 | 1 | IVPORTAL-78 | 14,15 | Resolved
Liferay UI Customization
Hide message displaying when can't assess a portlet or page | Hai Vu | 1 | 1 | IVPORTAL-198 | 15 | Planned
Apply ACL
Redesign new navigation bar following new mockup | Hoa Le | 3 | 3 | IVPORTAL-112 | 15 | Planned
Ticket systems
Implement Ticket portlet
Understand requirements | Dung Pham | 0.5 | 0.5 | IVPORTAL-121 | 15 | Resolved
Design UI | Dung Pham | 2 | 2 | IVPORTAL-122 | 15 | Resolved
Implement authenticate services and generate ticket | Dung Pham
Research configure database by Hibernate | Dung Pham | 2 | 2 | IVPORTAL-197 | 15 | In Progress
Call Portal service to authenticate user | Dung Pham | 3 | 3 | IVPORTAL-123 | 15 | Planned
Create ticket using Service Builder | Dung Pham | 2 | 2 | IVPORTAL-144 | 15 | Planned
Update ticket for the 1st usage | Dung Pham | 1 |  | IVPORTAL-169
Call Drive and get session | Dung Pham | 2 | 2 | IVPORTAL-124 | 15 | Planned
Invalidate a ticket | Dung Pham | 1 |  | IVPORTAL-125
UC12-Buy Online | [6 empty] | Never work before
Understand requirements | Khuong Nguyen | 0.5 | 0.5 | IVPORTAL-150 | 15 | Resolved
Generate Application PDF | Khuong Nguyen | 1 | 1 | IVPORTAL-154 | 15 | Planned
Design UI + Binding
Application Details screen | Khuong Nguyen | 4 | 4 | IVPORTAL-151 | 15 | In Progress
Implement attachment functions in Application Details screen | Khuong Nguyen | 2 | 2 | IVPORTAL-152 | 15 | Planned | Endpoint for attach and delete attach
Confirmation screen | Khuong Nguyen | 2 | 2 | IVPORTAL-153 | 15 | Planned
Acknowledement screen | Khuong Nguyen | 0.5 | 0.5 | IVPORTAL-155 | 15 | Planned
Process Pay Now button to navigate to Process Payment Screen | Khuong Nguyen | 0.5 | 0.5 | IVPORTAL-156 |  | Planned
After payment processing
Update status of Quote to ISSUED or SUBMITTED | Khuong Nguyen | 1 | 1 | IVPORTAL-157 |  | Planned
Generate PDF after payment succesffuly | Khuong Nguyen
Payment Slip | Khuong Nguyen | 0.5 | 0.5 | IVPORTAL-158 |  | Planned
ECover Note | Khuong Nguyen | 0.5 | 0.5 | IVPORTAL-159 |  | Planned
Epolicy | Khuong Nguyen | 0.5 | 0.5 | IVPORTAL-160 |  | Planned
Upgrade role for prospect after buying a policy successfully | Khuong Nguyen | 2 | 2 | IVPORTAL-161 |  | Planned
Send SMS/Email for payment status | Khuong Nguyen | 1.5 | 1.5 | IVPORTAL-162 |  | Planned
Call submission to send application to PAS | Khuong Nguyen | 5 |  | IVPORTAL-163
Design PDF template
Application form (draft version) | Hai Vu | 1 | 1 | IVPORTAL-164 | 15 | In Progress
Payment Slip | Hai Vu | 1 | 1 | IVPORTAL-165 | 15 | Planned | Implement in UC17
ECover Note | Hai Vu | 1 | 1 | IVPORTAL-166 | 15 | In Progress
Epolicy | Hai Vu | 1 | 1 | IVPORTAL-167 | 15 | Planned
Navigation between tabs | Khuong Nguyen | 0.5 | 0.5 | IVPORTAL-168 | 15 | Planned
My Workspace portlet
Design layout for Workspace portlet | Hoa Le | 3 | 3 | IVPORTAL-106 | 15 | In Progress
UC55-Prospect Module |  |  |  | IVPORTAL-108 | 14,15 | Planned
UI mockup | Hoa Le | 3.75 | 3.75 | IVPORTAL-107 | 14,15 | In Progress
BI Module
UI mockup
UC17-My Premium Payments | [6 empty] | Never work before
Understand requirements | Nhut Nguyen | 0.5 | 0.5 | IVPORTAL-134 | 15 | Resolved
Premium Due for Payment portlet (for Policy Owners)
Design UI + Binding | Nhut Nguyen | 2 | 2 | IVPORTAL-135 | 15 | Resolved
Call Backend to get policy list of login user | Nhut Nguyen | 1 | 1 | IVPORTAL-136 | 15 | Resolved
Pay Premium online portlet | [6 empty] | See 7.3 Online Premium Payment Screen
Design UI + Binding | Nhut Nguyen | 1 | 1 | IVPORTAL-137 | 15 | Planned | What's 7.4
Call backend to check validity of policy input | Nhut Nguyen | 1 | 1 | IVPORTAL-138 | 15 | Planned
Generate Payment Slip for successful payment screen | Nhut Nguyen | 0.5 | 0.5 | IVPORTAL-139 | 15 | Planned
Update status of policy upon successful payment | Nhut Nguyen | 1 | 1 | IVPORTAL-140 | 15 | Planned | Endpoint to udpate status of a policy to PAID Is IL auto run ISSUE batch for paid policy?
Send SMS/Email after payment successfully | Nhut Nguyen | 1 | 1 | IVPORTAL-141 | 15 | Planned
Design PDF template for Payment Slip | Nhut Nguyen | 1 | 1 | IVPORTAL-142 | 15 | Planned
Migrate Renewal portlet to V3
Support adding other drivers in Review screen | Minh Le | 2 | 2 | IVPORTAL-173 | 15 | Resolved
Call service to backend to check if a policy has claim or not and save to iPOS repository | Minh Le | 1 | 1 | IVPORTAL-178 |  |  | Create a list policy has claimed in a file, when input policy ID, check if this ID is in the list
Call service to backend to get policy status (check if a policy is now approved to renew by underwriter) and update to iPOS repository | Minh Le | 1.5 | 1.5 | IVPORTAL-179
Call service to update status of policy | Minh Le | 2 | 2 | IVPORTAL-180 | 15 | Planned
After determining if policy has claim or not (Renewal - Pending Review)
After navigating user to Payment process screen (Renewal - Pending Payment)
After payment is successfully (In force)
After payment processing
Call SMS/Email upon payment successfully | Minh Le | 1 | 1 | IVPORTAL-175 | 15 | Planned
Generate Payment slip | Minh Le | 0.5 | 0.5 | IVPORTAL-176 | 15 | Planned
Generate EPolicy | Minh Le | 0.5 | 0.5 | IVPORTAL-177 | 15 | Planned
Migrate Attachment functionality to V3 | Minh Le | 2 | 2 | IVPORTAL-181
Support save/refresh policy in iPOS repository | Minh Le | 1 | 0.5 | IVPORTAL-182
Implement compare functions apply for V3 document to display in Confirmation screen | Minh Le | 2 | 2 | IVPORTAL-183
Process Pay Now button to navigate to Process Payment Screen | Minh Le | 0.5 | 0.5 | IVPORTAL-184
Migrate Acknowledgement screen to V3 | Minh Le | 1.5 | 1.5 | IVPORTAL-174 | 15 | Planned
Migrate configuration of My Client portlet | Dang Nguyen | 3 | 1 | IVPORTAL-114 | 14,15 | In Progress
Migrate configuration ofClient List portlet | Dang Nguyen | 1 | 1 | IVPORTAL-115 | 14,15 | Planned
Migrate configuration of Policy List | Dang Nguyen | 1 | 1 | IVPORTAL-116 | 14,15 | In Progress
Update Payment Gateway to support payment processing for Pay Premium online function |  | 1
Rebind all policy detail screens with new Policy detail model | Qui Huynh | 1.5 | 1.5 | IVPORTAL-143 | 15 | Closed
Apply new user management
Apply ACL
Research to apply Access control to iPOS actions in Liferay | Phong Nguyen | 4 | 4 | IVPORTAL-146 | 15 | Planned
Support deployment of Login portlet for BA testing | Phong Nguyen | 2 | 2 | IVPORTAL-148 | 15 | Resolved
Support deployment portlet for MetLife demo | Phong Nguyen | 1 | 1 | IVPORTAL-194 | 15 | Planned
Support deployment static content for MetLife demo | Hai vu | 0.5 | 0.5 | IVPORTAL-195 | 15 | In Progress
Design services for MSP Mock
Write service in MSP mock to update policy detail for Motor and Life products | Long Hoang | 1.5 | 1.5 | IVPORTAL-170 | 15 | Closed
iPOS Portal core framework
Merge Portal portlet project into an core module in Common portlet project | Phong Nguyen | 3 | 2.5 | IVPORTAL-128 | 14,15 | Planned
Fix bugs
Policy detail load no data but detail screen still display label | Hai Vu | 0.25 | 0.25 | IVPORTAL-117 | 15 | Closed | Don't fix anymore
Hide Reset Change notification message
Config to hide portlet bar default
Design title bar for all portlets with configuration button
Research to add user into liferay
Relayout Personal Profile portlet | Dang Nguyen | 1.5 | 1.5 | IVPORTAL-196 | 15 | In Progress
Relayout Login portlet | Dang Nguyen | 2 | 2 | IVPORTAL-200 | 15 | Planned
Leading
Technical support | Bao Nguyen | 5 | 5 | IVPORTAL-191 | 15 | In Progress
Sprint planning | Bao Nguyen | 2 | 2 | IVPORTAL-192 | 15 | In Progress
Support deployment | Bao Nguyen | 3 | 3 | IVPORTAL-193 | 15 | In Progress

## Workload
| Long | Hai | Dung | Phong | Hoa | Khuong | Dang | Nhut | Minh | Qui
Sprint 15 | 10 | 6.5 | 11 | 7 | 9.75 | 11.5 | 8.5 | 9 | 7.5 | 10
19/03 | 8 | 11 | 8 |  | 8 |  | 8 |  | 8 | 5

## Sheet3
Main Flow
a) Unregistered Prospects register to buy online - accept declaration - pay successfully
b) Registered Policy Owners (PO) login to buy online - accept declaration - pay successfully
c) Registered Prospects login to buy online - accept declaration - pay successfully
Alternate Flow
a) Unregistered Prospects register to buy online - decline declaration
b) Unregistered Prospects register to buy online - accept declaration - pay unsuccessfully
c) Registered Prospects login to retrieve quote to buy online - accept declaration - pay successfully
d) Registered Prospects login to buy online - decline declaration
e) Registered Prospects login to buy online - accept declaration - pay unsuccessfully
f) Registered Prospects without login to buy online - accept declaration - pay successfully
g) Registered Prospects without login to buy online - accept declaration - pay unsuccessfully
h) Registered Prospects without login to buy online - decline declaration
i) Registered POs login to buy online - decline declaration
j) Registered POs login to buy online - accept declaration - pay unsuccessfully
k) Registered POs without login to buy online - accept declaration - pay successfully
l) Registered POs without login to buy online - accept declaration - pay unsuccessfully
m) Registered POs without login to buy online - decline declaration

## Endpoint
| Service name | Input | Output | Line Business
Sprint-15 | Service to check a policy has claim in last 12 months | Policy ID | Boolean | Motor
| Service to save policy/client detail to iPOS repository | Policy document |  | Motor, Life
| Service to check if policy/cilent detail saved in iPOS repository has been modified in backend | Policy ID | Boolean | Motor, Life
| Service to call Drive and get session | Ticket string | Drive Session string | N/A